## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | MERN App | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 to AC2. | Dream Team |  |  | Project Finish Date: |  | 2020-02-06 | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  | Project Start Date: |  | 2020-01-13
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 to cell BL4. Do not modify these cells. They are auto-updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 0 |  | January | [20 empty] | February | [27 empty] | March
Cells I5 to BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto-calculated. Do not modify these cells. Today’s date is outlined in Red (hex #AD3815) from today’s date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-01-13 to 2020-03-08
A scrollbar is in cells I6 to BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forwards or backwards in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart. | bar: 2020-01-13 to 2020-01-17; 2020-01-20 to 2020-01-24; 2020-01-27 to 2020-01-31; 2020-02-03 to 2020-02-05; 2020-02-07 to 2020-03-08
This row contains headers for the project schedule that follows below them. Navigate from B7 to BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues to cell BL7. All project timeline charting is auto-generated based on the category, start date and number of days entered in the Milestones table. | Milestone description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 to cell G9. Sample data is in cells B9 to G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Part B - Unit Testing - components
| Nav Bar | Goal | Chris | 0% | 2020-01-17 | 2 | F: 2
| General enquiry contact form | Goal |  | 0% | 2020-01-17 | 4 | F: 2; M: 2
| Booking Form | Goal |  | 0% | 2020-01-20 | 8 | M: 2; T: 2; W: 2; T: 2; F: 2; M: 2
| Patient Registraton Form | Goal |  | 0% | 2020-01-20 | 3 | M: 2; T: 2; W: 2
| Admin dashboard - appointment list | Goal |  | 0% | 2020-01-27 | 2
| Login Form with JWT authentication | Goal |  | 0% | 2020-01-17 | 6 | F: 2; M: 2; T: 2; W: 2
Enter Project information starting in cell B9 to cell G9. Sample data is in cells B9 to G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Part B - Coding - Components
| Nav Bar | Goal | Chris | 0% | 2020-01-17 | 2 | F: 2
| General enquiry contact form | Goal |  | 0% | 2020-01-17 | 4 | F: 2; M: 2
| Booking Form | Goal |  | 0% | 2020-01-20 | 8 | M: 2; T: 2; W: 2; T: 2; F: 2; M: 2
| Patient Registraton Form | Goal |  | 0% | 2020-01-22 | 2 | W: 2; T: 2
| Stylesheet | Goal |  | 0% | 2020-01-22 | 2 | W: 2; T: 2
| Staff Profile with image upload | Goal |  | 0% | 2020-01-24 | 4 | F: 2; M: 2
| List of current day's appointments for admin user | Goal |  | 0% | 2020-01-27 | 2 | M: 2; T: 2
|  | Goal |  | 0% | 2020-01-29 | 2
| List of user's appointments | Goal |  | 0% | 2020-01-28 | 2 | T: 2; W: 2
| User Information | Goal |  | 0% | 2020-01-30 | 2 | T: 2; F: 2
| Login Form | Goal |  | 0% | 2020-01-17 | 6 | F: 2; M: 2; T: 2; W: 2
Enter Project information starting in cell B9 to cell G9. Sample data is in cells B9 to G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Part B - Coding - Pages
| Home Page | Goal |  | 0% | 2020-01-17 | 4 | F: 2; M: 2
| Contact Page with Redux Form and CRUD function | Goal |  | 0% | 2020-01-17 | 4 | F: 2; M: 2
| Booking Page with Redux Form | Goal |  | 0% | 2020-01-28 | 1 | T: 2
| Staff profile page with CRUD function & image upload | Goal |  | 0% | 2020-01-28 | 1 | T: 2
| User Dashboard with CRUd for user info & appointments | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| Admin Dashboard with full CRUD | Goal |  | 0% | 2020-01-29 | 2 | W: 2; T: 2
|  |  |  | 0% | 31/02/20 | 1
Part B - Coding - Back end
| Routing | Goal |  | 0% | 2020-01-17 | 1 | F: 2
| Authentication - JSON web token | Goal |  | 0% | 2020-01-17 | 6 | F: 2; M: 2; T: 2; W: 2
| Schemas/Models | Goal |  | 0% | 2020-01-17 | 1 | F: 2
| Controllers | Goal |  | 0% | 2020-01-17 | 14 | F: 2; M: 2; T: 2; W: 2; T: 2; F: 2; M: 2; T: 2; W: 2; T: 2
| Set Up Mail Gun | Goal |  | 0% | 2020-01-20 | 2 | M: 2; T: 2
Part B - Hosting
| Deploy backend to Heroku | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| Deploy frontend to Netlify | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| Create MongoDB Atlas database | Goal |  | 0% | 2020-01-17 | 1 | F: 2
Part B - System Integration Testing - Development
| User can create an account | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| JWT authentication | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| User/admin dashboard displays correct information | Goal |  | 0% | 2020-02-03 | 1 | M: 2
| User CRUD | Goal |  | 0% | 2020-02-03 | 2 | M: 2; T: 2
| Admin CRUD - users, staff profile, appointments | Goal |  | 0% | 2020-02-03 | 2 | M: 2; T: 2
Part B - System Integration Testing - Production
| User can create an account | Goal |  | 0% | 2020-01-31 | 1 | F: 2
| JWT authentication | Goal |  | 0% | 2020-01-31 | 4 | F: 2; M: 2
| User/admin dashboard displays correct information | Goal |  | 0% | 2020-02-03 | 1 | M: 2
| User CRUD | Goal |  | 0% | 2020-02-03 | 2 | M: 2; T: 2
| Admin CRUD - users, staff profile, appointments | Goal |  | 0% | 2020-02-03 | 2 | M: 2; T: 2
Part B - User Acceptance Testing
| Write Test Scripts | Goal |  | 0% | 2020-02-03 | 1 | M: 2
| Development environment | Goal |  | 0% | 2020-02-04 | 1 | T: 2
| Production Environment | Goal |  | 0% | 2020-02-05 | 1 | W: 2
Part B - Finishing Touches
| Fix bugs/adjustments from user feedback | Goal |  | 0% | 2020-02-05 | 2 | W: 2; T: 2
| Finalize readme documentation | Goal |  | 0% | 2020-02-05 | 2 | W: 2; T: 2
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do in tandem with the building of the actual components

## Team
Chris
Heng
Nhan

## About
About this template
This template provides a simple way to create a Gantt chart to help visualise and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a per cent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is colour-coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for screen readers
There are two worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you to the information in that row. Each subsequent step continues in cell A2, A3 and so on, unless otherwise explicitly directed. For example, instruction text might say “continue to cell A6” for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.